## Sheet1
|  |  | Project Plan- Dating APP Development |  |  |  | `
#number | Module | Sub-module | Tasks | Expected timeline | Date start | Date end | Remarks
| Design Phase | PSD Design | Complete PSD design of all screens including Home, Profile, Messages, etc | 10 | 2019-07-15 | 2019-07-26
|  | Design Integration | Once confirmed PSD design then integrate the design into Android studio and send you the APK for the feedback | 14 | 2019-07-29 | 2019-08-16
| Database Management |  | DB schema designing, integrate database, create tables and joins etc | 3 | 2019-08-19 | 2019-08-21
App Screens
|  | Registration | Social media registration | 3 | 2019-08-22 | 2019-08-26
Traditional registration
|  | Login | By social media
By Traditional login form to enter the email id and valid password
|  | Forgot Password | System generate passwrd will send on registred email id
|  | Search profile | Normal search: Search by location, name, gender, age, etc | 2 | 2019-08-27 | 2019-08-28
|  |  | Advanced search: Nearby, Online users, Religion, Interests, Viewed and Favorite | 2 | 2019-09-02 | 2019-09-03
|  | Home screen | Search bar with list of system sugested profiles. Every profile with Like and Unlike option. | 2 | 2019-08-29 | 2019-08-30
|  | Profile screen | To check the complete detilas of other members with like/unlike, block, report user and send | 5 | 2019-09-04 | 2019-09-10
|  | Report user | Member can complaint to admin in case of abusing
|  | Chat | List of friends | 10 | 2019-10-08 | 2019-10-21
Chat history, send and receive message
Send text and voice notes, files, location, contact details, videos, audios, pictures, emoticons etc.
|  | My Account | Manage personal information and upload the pick | 10 | 2019-09-24 | 2019-10-07
Change password
Recent maches
Set preference and get notification on screen when system find profile according to preference
Package screen: Check all the package plan and can select any package
Change plan: Upgrade/downgrade
Payment history
|  | Match making | Match making algorithm creation and integration | 5 | 2019-09-11 | 2019-09-17
|  | Payment gateway integration | Single payment gateway integration TBD | 4 | 2019-09-18 | 2019-09-23
|  | Notifications | a. After registration b. New subscription plan added c. New member registered on app that match with preference d. New message receive e. Profile like/unlike f. Before plan expired | 4 | 2019-10-02 | 2019-10-07
|  | FAQ |  | 2 | 2019-10-22 | 2019-10-23
Blog
| API development |  |  |  | 2019-08-19 | 2019-10-28
Admin Panel
|  | Login |  | 1 | 2019-08-22 | 2019-08-22
|  | Admin Dashboard |  | 1 | 2019-08-23 | 2019-08-23
|  | User Manager | The admin can see all the registered user on the app | 2 | 2019-08-26 | 2019-08-27
|  | Payment Manager | The admin can see the members detail, plans, purchased date, expire date etc. Also will have an option to suspend the account in case admin gets report against the member. | 4 | 2019-08-28 | 2019-09-02
|  | Package Manager | Add/edit/delete new subscription pack and decide period and price. | 3 | 2019-09-03 | 2019-09-05
|  | Report User Manager | List of complaints against the members with option to remark on the complaint. | 1 | 2019-09-06 | 2019-09-06
|  | Analytic Reports | User wise report with sorting feature (sort by name, dates) | 3 | 2019-09-09 | 2019-09-11
|  |  | Sales report with sorting feature (sort by package name, date) | 4 | 2019-09-24 | 2019-09-27
|  | Push Notifications |  | 3 | 2019-10-01 | 2019-10-03
|  | Content Manager | Add/edit/delete content pages | 1 | 2019-10-07 | 2019-10-07
|  | Miscellenous |  | 4 | 2019-10-24 | 2019-10-29
| Testing |  |  | 5 | 2019-10-30 | 2019-11-05
| Beta Testing |  |  | 7 | 2019-11-06 | 2019-11-14
| Deployment |  |  | 2 | 2019-11-15 | 2019-11-18
Note: These are expected dates and it could be only finished on time if we receive timely feedback from your end. Also above shared modules would be worked on parallel basis. So it will reduce the overall number of days.
Timeline: 3 months i.e. 90 days
It will be continous process through out the app development. So can't add specific timeline for this.